## PICS
TIE-IN WORKABLE 8 DWG
[12 empty] | PAT, CAN ISSUE | [10 empty] | HD | SMP1 | SMP1
NO | TIE-IN C/N | ISO DWG | ITEM NO | Mat Code | Item | Size1 | Size2 | Sch1 | Sch2 | Description | Stock | Vaild | Moudule | ISO DWG No | Deleted | Rev | Unit | Area | System | Class | BM | W.G | PreBooked | Booking | Issued | Remain | Remark | Paint Code | COMMENT SMP1 MATERIAL TEAM | STATUS | ACTION BY | PAINT REQ NO | PAINT REQ DATE
1 | 6 | M230575189_A863-2_SB_LPC-24311-099_6 | 6 | M230575189 | FIG 8 BL | 2 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 285 | 275 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Send for Paint(RBH-0079),(17-Sep send) | PAINT SHOP | PAINT SHOP | RBH-0079 | 2025-09-17
| 6 | M192030561_A863-2_SB_LPC-24311-099_7 | 7 | M192030561 | ROUND PLUG | 1 |  |  |  | CS A105 MTE B16.11 | 4109 | 4107 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Lay-a Store | READY FOR USE
| 6 | M280156151_A863-2_SB_LPC-24311-099_8 | 8 | M280156151 | GSKT SPR WND | 2 | 0 | CL150 | 0 | 316L SS WND GRAPH FILL 316L SS I/R CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 571 | 571 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 5 | SMP-1 | 0 | 0 | 0 | 5 |  | - | Prebooked Balance
| 6 | M264052297_A863-2_SB_LPC-24311-099_9 | 9 | M264052297 | GSKT SPR WND | 2 |  | CL150 |  | 316L SS WND GRAPH FILL CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 3854 | 3767 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 1 | SMP-1 | 0 | 1 | 0 | 0 |  | - | Booking Finish but not yet Received | TO BE ISSUED | SMP1 MATERIAL
| 6 | M230515170_A863-2_SB_LPC-24311-099_10 | 10 | M230515170 | STUD B W/H HEX N | 0.625 | 90 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 12180 | 12044 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 16 | SMP-1 | 0 | 0 | 16 | 0 |  | - | Lay-a Store | READY FOR USE
| 6 | M230578304_A863-2_SB_LPC-24311-099_11 | 11 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 4 | SMP-1 | 0 | 0 | 4 | 0 |  | - | Lay-a Store | READY FOR USE
| 6 | M212915447_A863-2_SB_LPC-24311-099_12 | 12 | M212915447 | GATE VA LP | 2 |  |  |  | CS A216-WCB CL150 RF B16.5 API 600 Trim No.5 BB OS&Y-RS FLEX WDG Hand Wheel | 386 | 378 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 2 | SMP-1 | 2 | 0 | 0 | 2 |  | APCS-2C | Yesterday Booking Need to Collect from WH |  | DULI RE-CHECK
| 6 | M191110503_A863-2_SB_LPC-24311-099_13 | 13 | M191110503 | BL FLG | 2 |  | CL150 |  | CS A105 CL150 RF B16.5 | 213 | 195 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Send for Paint (RBH-0091),(30Oct-Send) | PAINT SHOP | PAINT SHOP | RBH-0091 | 2025-10-30
| 6 | KSH-C2_A863-2_SB_LPC-24311-099_14 | 14 | KSH-C2 | SUPPORT |  |  |  |  | SUPPORT | 0 | 0 | SB | A863-2_SB_LPC-24311-099 |  | A0 |  | A863-2 | LPC | 1CS2U01 | 1 | SMP-1 | 0 | 0 | 0 | 1 |  | - | SUPPORT MATERIAL | PAINT SHOP | PAINT SHOP
2 | 8 | M230575191_A863-2_SB_N-24302-099_5 | 5 | M230575191 | FIG 8 BL | 3 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 70 | 70 | SB | A863-2_SB_N-24302-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint(RBH-0079),(17-Sep Send) | PAINT SHOP | PAINT SHOP | RBH-0079 | 2025-09-17
| 8 | M192030561_A863-2_SB_N-24302-099_6 | 6 | M192030561 | ROUND PLUG | 1 |  |  |  | CS A105 MTE B16.11 | 4109 | 4107 | SB | A863-2_SB_N-24302-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Lay-a Store | READY FOR USE
| 8 | M264052300_A863-2_SB_N-24302-099_7 | 7 | M264052300 | GSKT SPR WND | 3 |  | CL150 |  | 316L SS WND GRAPH FILL CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 1231 | 1222 | SB | A863-2_SB_N-24302-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 5 | SMP-1 | 0 | 5 | 0 | 0 |  |  | Booking Finish but not yet Received | TO BE ISSUED | SMP1 MATERIAL
| 8 | M230578304_A863-2_SB_N-24302-099_8 | 8 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | A863-2_SB_N-24302-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 12 | SMP-1 | 0 | 0 | 12 | 0 |  |  | Lay-a Store | READY FOR USE
| 8 | M230718054_A863-2_SB_N-24302-099_9 | 9 | M230718054 | STUD B W/H HEX N | 0.625 | 105 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 1308 | 1296 | SB | A863-2_SB_N-24302-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 4 | SMP-1 | 0 | 0 | 4 | 0 |  |  | Lay-a Store | READY FOR USE
| 8 | M238710449_A863-2_SB_N-24302-099_10 | 10 | M238710449 | BALL VA FLG LP | 3 |  |  |  | CS A216-WCB CL150 RF B16.5 API 6D Trim 316 RTFE FL. Side Entry RB Lever | 8 | 8 | SB | A863-2_SB_N-24302-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 2 | SMP-1 | 0 | 0 | 0 | 2 |  | APCS-1D | Prebooked Balance |  | DULI RE-CHECK
| 8 | M191110508_A863-2_SB_N-24302-099_11 | 11 | M191110508 | BL FLG | 3 |  | CL150 |  | CS A105 CL150 RF B16.5 | 40 | 33 | SB | A863-2_SB_N-24302-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 1 | SMP-1 | 1 | 0 | 0 | 1 |  | APCS-1D | Yesterday Booking Need to Collect from WH |  | DULI RE-CHECK
3 | 9 | M230575189_A863-2_SB_N-24312-099_5 | 5 | M230575189 | FIG 8 BL | 2 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 285 | 275 | SB | A863-2_SB_N-24312-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint(RBH-0079),(17-Sep send) | PAINT SHOP | PAINT SHOP | RBH-0079 | 2025-09-17
| 9 | M192030561_A863-2_SB_N-24312-099_6 | 6 | M192030561 | ROUND PLUG | 1 |  |  |  | CS A105 MTE B16.11 | 4109 | 4107 | SB | A863-2_SB_N-24312-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Lay-a Store | READY FOR USE
| 9 | M264052297_A863-2_SB_N-24312-099_7 | 7 | M264052297 | GSKT SPR WND | 2 |  | CL150 |  | 316L SS WND GRAPH FILL CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 3854 | 3767 | SB | A863-2_SB_N-24312-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 5 | SMP-1 | 0 | 5 | 0 | 0 |  |  | Booking Finish but not yet Received | TO BE ISSUED | SMP1 MATERIAL
| 9 | M230578304_A863-2_SB_N-24312-099_8 | 8 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | A863-2_SB_N-24312-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 4 | SMP-1 | 0 | 0 | 4 | 0 |  |  | Lay-a Store | READY FOR USE
| 9 | M230515170_A863-2_SB_N-24312-099_9 | 9 | M230515170 | STUD B W/H HEX N | 0.625 | 90 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 12180 | 12044 | SB | A863-2_SB_N-24312-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 12 | SMP-1 | 0 | 0 | 12 | 0 |  |  | Lay-a Store | READY FOR USE
| 9 | M191110503_A863-2_SB_N-24312-099_10 | 10 | M191110503 | BL FLG | 2 |  | CL150 |  | CS A105 CL150 RF B16.5 | 213 | 195 | SB | A863-2_SB_N-24312-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint (RBH-0091),(30Oct-Send) | PAINT SHOP | PAINT SHOP | RBH-0091 | 2025-10-30
| 9 | M238710447_A863-2_SB_N-24312-099_11 | 11 | M238710447 | BALL VA FLG LP | 2 |  |  |  | CS A216-WCB CL150 RF B16.5 API 6D Trim 316 RTFE FL. Side Entry RB Lever | 32 | 30 | SB | A863-2_SB_N-24312-099 |  | A0 |  | A863-2 | N | 1CS1P01 | 2 | SMP-1 | 0 | 0 | 0 | 2 |  | APCS-1D | Prebooked Balance |  | DULI RE-CHECK
4 | 10 | M230575189_A863-2_SB_PA-24293-099_3 | 3 | M230575189 | FIG 8 BL | 2 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 285 | 275 | SB | A863-2_SB_PA-24293-099 |  | A0 |  | A863-2 | PA | 1CS2P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint(RBH-0079),(17-Sep send) | PAINT SHOP | PAINT SHOP | RBH-0079 | 2025-09-17
| 10 | M264052297_A863-2_SB_PA-24293-099_4 | 4 | M264052297 | GSKT SPR WND | 2 |  | CL150 |  | 316L SS WND GRAPH FILL CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 3854 | 3767 | SB | A863-2_SB_PA-24293-099 |  | A0 |  | A863-2 | PA | 1CS2P01 | 4 | SMP-1 | 0 | 4 | 0 | 0 |  |  | Booking Finish but not yet Received | TO BE ISSUED | SMP1 MATERIAL
| 10 | M230515170_A863-2_SB_PA-24293-099_5 | 5 | M230515170 | STUD B W/H HEX N | 0.625 | 90 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 12180 | 12044 | SB | A863-2_SB_PA-24293-099 |  | A0 |  | A863-2 | PA | 1CS2P01 | 8 | SMP-1 | 0 | 0 | 8 | 0 |  |  | Lay-a Store | READY FOR USE
| 10 | M230578304_A863-2_SB_PA-24293-099_6 | 6 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | A863-2_SB_PA-24293-099 |  | A0 |  | A863-2 | PA | 1CS2P01 | 4 | SMP-1 | 0 | 0 | 4 | 0 |  |  | Lay-a Store | READY FOR USE
| 10 | M238710447_A863-2_SB_PA-24293-099_7 | 7 | M238710447 | BALL VA FLG LP | 2 |  |  |  | CS A216-WCB CL150 RF B16.5 API 6D Trim 316 RTFE FL. Side Entry RB Lever | 32 | 30 | SB | A863-2_SB_PA-24293-099 |  | A0 |  | A863-2 | PA | 1CS2P01 | 1 | SMP-1 | 0 | 0 | 0 | 1 |  | APCS-1D | Prebooked Balance |  | DULI RE-CHECK
| 10 | M191110503_A863-2_SB_PA-24293-099_8 | 8 | M191110503 | BL FLG | 2 |  | CL150 |  | CS A105 CL150 RF B16.5 | 213 | 195 | SB | A863-2_SB_PA-24293-099 |  | A0 |  | A863-2 | PA | 1CS2P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint (RBH-0091),(30Oct-Send) | PAINT SHOP | PAINT SHOP | RBH-0091 | 2025-10-30
5 | 21 | M230575189_A863-3B_SB_N-25075-099_6 | 6 | M230575189 | FIG 8 BL | 2 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 285 | 275 | SB | A863-3B_SB_N-25075-099 |  | A0 |  | A863-3B | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint(RBH-0079),(17-Sep send) | PAINT SHOP | PAINT SHOP | RBH-0079 | 2025-09-17
| 21 | M192030561_A863-3B_SB_N-25075-099_7 | 7 | M192030561 | ROUND PLUG | 1 |  |  |  | CS A105 MTE B16.11 | 4109 | 4107 | SB | A863-3B_SB_N-25075-099 |  | A0 |  | A863-3B | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Lay-a Store | READY FOR USE
| 21 | M264052297_A863-3B_SB_N-25075-099_8 | 8 | M264052297 | GSKT SPR WND | 2 |  | CL150 |  | 316L SS WND GRAPH FILL CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 3854 | 3767 | SB | A863-3B_SB_N-25075-099 |  | A0 |  | A863-3B | N | 1CS1P01 | 5 | SMP-1 | 0 | 5 | 0 | 0 |  |  | Booking Finish but not yet Received | TO BE ISSUED | SMP1 MATERIAL
| 21 | M230578304_A863-3B_SB_N-25075-099_9 | 9 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | A863-3B_SB_N-25075-099 |  | A0 |  | A863-3B | N | 1CS1P01 | 4 | SMP-1 | 0 | 0 | 4 | 0 |  |  | Lay-a Store | READY FOR USE
| 21 | M230515170_A863-3B_SB_N-25075-099_10 | 10 | M230515170 | STUD B W/H HEX N | 0.625 | 90 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 12180 | 12044 | SB | A863-3B_SB_N-25075-099 |  | A0 |  | A863-3B | N | 1CS1P01 | 12 | SMP-1 | 0 | 0 | 12 | 0 |  |  | Lay-a Store | READY FOR USE
| 21 | M191110503_A863-3B_SB_N-25075-099_11 | 11 | M191110503 | BL FLG | 2 |  | CL150 |  | CS A105 CL150 RF B16.5 | 213 | 195 | SB | A863-3B_SB_N-25075-099 |  | A0 |  | A863-3B | N | 1CS1P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint (RBH-0091),(30Oct-Send) | PAINT SHOP | PAINT SHOP | RBH-0091 | 2025-10-30
| 21 | M238710447_A863-3B_SB_N-25075-099_12 | 12 | M238710447 | BALL VA FLG LP | 2 |  |  |  | CS A216-WCB CL150 RF B16.5 API 6D Trim 316 RTFE FL. Side Entry RB Lever | 32 | 30 | SB | A863-3B_SB_N-25075-099 |  | A0 |  | A863-3B | N | 1CS1P01 | 2 | SMP-1 | 0 | 0 | 0 | 2 |  | APCS-1D | Prebooked Balance |  | DULI RE-CHECK
6 | 22 | M230575189_A863-3B_SB_PA-24002-099_1 | 1 | M230575189 | FIG 8 BL | 2 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 285 | 275 | SB | A863-3B_SB_PA-24002-099 |  | A0 |  | A863-3B | PA | 1CS2P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint(RBH-0079),(17-Sep send) | PAINT SHOP | PAINT SHOP | RBH-0079 | 2025-09-17
| 22 | M264052297_A863-3B_SB_PA-24002-099_2 | 2 | M264052297 | GSKT SPR WND | 2 |  | CL150 |  | 316L SS WND GRAPH FILL CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 3854 | 3767 | SB | A863-3B_SB_PA-24002-099 |  | A0 |  | A863-3B | PA | 1CS2P01 | 3 | SMP-1 | 0 | 3 | 0 | 0 |  |  | Booking Finish but not yet Received | TO BE ISSUED | SMP1 MATERIAL
| 22 | M230578304_A863-3B_SB_PA-24002-099_3 | 3 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | A863-3B_SB_PA-24002-099 |  | A0 |  | A863-3B | PA | 1CS2P01 | 4 | SMP-1 | 0 | 0 | 4 | 0 |  |  | Lay-a Store | READY FOR USE
| 22 | M230515170_A863-3B_SB_PA-24002-099_4 | 4 | M230515170 | STUD B W/H HEX N | 0.625 | 90 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 12180 | 12044 | SB | A863-3B_SB_PA-24002-099 |  | A0 |  | A863-3B | PA | 1CS2P01 | 4 | SMP-1 | 0 | 0 | 4 | 0 |  |  | Lay-a Store | READY FOR USE
| 22 | M191110503_A863-3B_SB_PA-24002-099_5 | 5 | M191110503 | BL FLG | 2 |  | CL150 |  | CS A105 CL150 RF B16.5 | 213 | 195 | SB | A863-3B_SB_PA-24002-099 |  | A0 |  | A863-3B | PA | 1CS2P01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-1D | Send for Paint (RBH-0091),(30Oct-Send) | PAINT SHOP | PAINT SHOP | RBH-0091 | 2025-10-30
| 22 | M238710447_A863-3B_SB_PA-24002-099_6 | 6 | M238710447 | BALL VA FLG LP | 2 |  |  |  | CS A216-WCB CL150 RF B16.5 API 6D Trim 316 RTFE FL. Side Entry RB Lever | 32 | 30 | SB | A863-3B_SB_PA-24002-099 |  | A0 |  | A863-3B | PA | 1CS2P01 | 1 | SMP-1 | 0 | 0 | 0 | 1 |  | APCS-1D | Prebooked Balance |  | DULI RE-CHECK
7 | 25 | M230575191_A870-1_SB_LPS-24259-099_5 | 5 | M230575191 | FIG 8 BL | 3 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 70 | 70 | SB | A870-1_SB_LPS-24259-099 |  | C1 |  | A870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Non Painted Lay-a Store | PAINT TO BE SENT | SMP1 MATERIAL
| 25 | M192030561_A870-1_SB_LPS-24259-099_6 | 6 | M192030561 | ROUND PLUG | 1 |  |  |  | CS A105 MTE B16.11 | 4109 | 4107 | SB | A870-1_SB_LPS-24259-099 |  | C1 |  | A870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Lay-a Store | READY FOR USE
| 25 | M280156153_A870-1_SB_LPS-24259-099_7 | 7 | M280156153 | GSKT SPR WND | 3 | 0 | CL150 | 0 | 316L SS WND GRAPH FILL 316L SS I/R CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 170 | 170 | SB | A870-1_SB_LPS-24259-099 |  | C1 |  | A870-1 | LPS | 1CS1U01 | 5 | SMP-1 | 0 | 0 | 0 | 5 |  | - | Prebooked Balance |  | DULI RE-CHECK
| 25 | M230718054_A870-1_SB_LPS-24259-099_8 | 8 | M230718054 | STUD B W/H HEX N | 0.625 | 105 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 1308 | 1296 | SB | A870-1_SB_LPS-24259-099 |  | C1 |  | A870-1 | LPS | 1CS1U01 | 4 | SMP-1 | 4 | 0 | 0 | 4 |  | - | Lay-a Store | READY FOR USE
| 25 | M230578304_A870-1_SB_LPS-24259-099_9 | 9 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | A870-1_SB_LPS-24259-099 |  | C1 |  | A870-1 | LPS | 1CS1U01 | 12 | SMP-1 | 0 | 12 | 0 | 0 |  | - | Lay-a Store | READY FOR USE
| 25 | M191110508_A870-1_SB_LPS-24259-099_10 | 10 | M191110508 | BL FLG | 3 |  | CL150 |  | CS A105 CL150 RF B16.5 | 40 | 33 | SB | A870-1_SB_LPS-24259-099 |  | C1 |  | A870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Yesterday Booking Need to Collect from WH |  | DULI RE-CHECK
| 25 | M367335618_A870-1_SB_LPS-24259-099_11 | 11 | M367335618 | GATE VA LP | 3 | 0 | 0 | 0 | CS A216-WCB CL150 RF B16.5 API 600 Trim No.5 BB OS&Y-RS FLEX WDG Hand Wheel for Safety | 12 | 10 | SB | A870-1_SB_LPS-24259-099 |  | C1 |  | A870-1 | LPS | 1CS1U01 | 2 | SMP-1 | 2 | 0 | 0 | 2 |  | APCS-2C | Yesterday Booking Need to Collect from WH |  | DULI RE-CHECK
8 | 40 | M238840827_S870-1_SB_LPS-24262-099_2 | 2 | M238840827 | 75mm NPL | 1 |  | S-XS |  | CS A106-B SMLS OB x OP B36.10M | 0 | 0 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 0 | 1 |  | APCS-2C | Lay-a Store
| 40 | M229869532_S870-1_SB_LPS-24262-099_4 | 4 | M229869532 | GATE VA SE | 1 |  |  |  | CS A105 CL800 SWE x FTE B16.11 API 602 STD Bore Trim No.5 BB OS&Y-RS SLD WDG Hand Wheel | 1958 | 1852 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 0 | 1 |  | APCS-2C | Yesterday Booking Need to Collect from WH |  | DULI RE-CHECK
| 40 | M230575189_S870-1_SB_LPS-24262-099_5 | 5 | M230575189 | FIG 8 BL | 2 |  |  |  | CS A516-Gr.70 CL150 RF B16.48 & PJT-STD | 285 | 275 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Send for Paint(RBH-0079),(17-Sep send) | PAINT SHOP | PAINT SHOP | RBH-0079 | 2025-09-17
| 40 | M192030561_S870-1_SB_LPS-24262-099_6 | 6 | M192030561 | ROUND PLUG | 1 |  |  |  | CS A105 MTE B16.11 | 4109 | 4107 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Lay-a Store | READY FOR USE
| 40 | M280156151_S870-1_SB_LPS-24262-099_7 | 7 | M280156151 | GSKT SPR WND | 2 | 0 | CL150 | 0 | 316L SS WND GRAPH FILL 316L SS I/R CS O/R CL150 RF B16.20 4.5MM THK (3.2MM RING) | 571 | 571 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 5 | SMP-1 | 0 | 0 | 0 | 5 |  | - | Prebooked Balance |  | DULI RE-CHECK
| 40 | M230515170_S870-1_SB_LPS-24262-099_8 | 8 | M230515170 | STUD B W/H HEX N | 0.625 | 90 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 12180 | 12044 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 12 | SMP-1 | 0 | 12 | 0 | 0 |  | - | Lay-a Store | READY FOR USE
| 40 | M230578304_S870-1_SB_LPS-24262-099_9 | 9 | M230578304 | STUD B W/H HEX N | 0.625 | 100 |  |  | AS A193 GR B7 / A194 GR 2H B18.31.2/B18.2.2 CERAMIC-FLUOROPOLYMER COATED | 8568 | 8416 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 4 | SMP-1 | 0 | 4 | 0 | 0 |  | - | Lay-a Store | READY FOR USE
| 40 | M367335617_S870-1_SB_LPS-24262-099_10 | 10 | M367335617 | GATE VA LP | 2 | 0 | 0 | 0 | CS A216-WCB CL150 RF B16.5 API 600 Trim No.5 BB OS&Y-RS FLEX WDG Hand Wheel for Safety | 29 | 27 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 2 | SMP-1 | 0 | 2 | 0 | 0 |  | APCS-2C | Paint Code Wrong (Actual Paint 11C) | TO BE ISSUED | SMP1 MATERIAL
| 40 | M191110503_S870-1_SB_LPS-24262-099_11 | 11 | M191110503 | BL FLG | 2 |  | CL150 |  | CS A105 CL150 RF B16.5 | 213 | 195 | SB | S870-1_SB_LPS-24262-099 |  | D0 |  | S870-1 | LPS | 1CS1U01 | 1 | SMP-1 | 0 | 0 | 1 | 0 |  | APCS-2C | Send for Paint (RBH-0091),(30Oct-Send) | PAINT SHOP | PAINT SHOP | RBH-0091 | 2025-10-30
|  | S870-1_SB_LPS-24262-099 | Shop/2,4

## Sheet1
VALVES BOOKED SUMMARY
Booking Date | ITEM | MAT.CODE | Size | BM | ISO | Paint Code | Actual Paint Code
2025-10-14 | GATE VA LP | M212915447 | 2 | 2 | A863-2_SB_LPS-24308-099 | APCS-11C | APCS-2C
2025-11-08 | GATE VA LP | M367335617 | 2 | 2 | S870-1_SB_LPS-24262-099 | APCS-2C | APCS-11C
2025-11-11 | GATE VA LP | M212915447 | 2 | 2 | A863-2_SB_LPC-24311-099 | APCS-2C
2025-11-11 | GATE VA LP | M212915447 | 2 | 2 | A863-3B_SB_LPS-24320-099 | APCS-11C
2025-11-11 | GATE VA LP | M367335618 | 3 | 2 | A870-1_SB_LPS-24259-099 | APCS-2C
2025-11-11 | GATE VA SE | M229869532 | 1 | 1 | A870-1_SB_N-24105-099 | APCS-1D